## Sheet1
| DRAFT - Facilities Planning Committee |  | Annual Timeline | 2018-19 | [11 empty] | Annual Timeline
| Activity | July | August | September | October | November | December | January | February | March | April | May | June | July | August
1 | Accreditation: Review Standard III B | bar: 2018-19 September
2 | Review Committee Purpose, Charge & Operating Agreement | bar: 2018-19 September
4 | Review Facilities related BPs and APs & recommend updates if needed | bar: 2018-19 October
5 | Review the 5-Year Capital Plan | bar: 2018-19 November
6 | Review Building Standards | bar: 2018-19 November
7 | Review ADA Transition Plan for progress updates | bar: 2018-19 December
8 | Review Annual Landscape Plan | bar: 2018-19 December
9 | Develop a prioritized list of resource requests for Budget Planning Committee | bar: 2018-19 January to 2018-19 February
10 | Review Furniture Standards | bar: 2018-19 February
11 | Committee self-evaluation survey and submit to IR | bar: 2018-19 March
12 | Review Facilities Master Plan (FMP) for updates | bar: 2018-19 March
13 | Send out Facilities Survey to Constituent Groups | bar: 2018-19 March
14 | Review FMP, Ed Master Plan & CR Annual Plan for consistency | bar: 2018-19 April
15 | Review results of Budget Planning Committee resource requests | bar: 2018-19 April
16 | Select meeting day/time and committee members for next year | bar: 2018-19 April to 2018-19 May
17 | Information about Deferred Maintenance program | bar: 2018-19 May
18 | Update on Capital Projects, State & District funded | bar: 2018-19 September to 2018-19 August
Facilities Master Plan Update Timeline
Review Plan, determine areas to update and data needed, divide work among committee members | bar: 2018-19 September
Members work on assigned sections | bar: 2018-19 October
Draft of updates availabe to Committee Members | bar: 2018-19 October
Refind Draft, determine additional research or information | bar: 2018-19 November
Finalize draft plan | bar: 2018-19 December; 2018-19 February
Circulate Plan: Expanded Cabinet, Cabinet, Deans, Insturctional Council, SLUG, CSEA, Management Council | bar: 2018-19 March
Academic Senate | bar: 2018-19 April
Board of Trustees | bar: 2018-19 May